## Overview (hidden)
[7 empty] | Focus Area | #REF! |  | #REF! |  | #REF! |  | #REF! |  | Increase Detection |  | Increase Detection |  | Increase Detection |  | Increase Detection |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Streamline Compliance |  | Streamline Compliance |  |  | Streamline Compliance |  |  | Build Security Organization / Skills |  | Build Security Organization / Skills |  | Build Security Organization / Skills
IT Security Initiative | [7 empty] | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | 0 | #REF! | 0
Progress KPI Reporting 2020 | [7 empty] | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | 1 | #REF! | 1
as of 04.09.2020 | [7 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Board Members | H Ressort | ITC Mapping |  | Group Iso Function | OEs ID | CIM ID | OE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
.
Bäte | H1 CEO | 1 | Allianz SE, Allianz Europe | Shared Services | 1 | AZSE | Allianz SE | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 1 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Thallinger | H3 Investments Management | 2 | Allianz Investment | Shared Services | 2 | ADEUS | ADEUS Aktienregister-Service-GmbH | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Europe 3 | 3 | AGL | Allianz Global Life | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 4 | AIM | Allianz Investment Management (AIM) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 5 | ARE | Allianz Real Estate (ARE) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 6 | IDS | Investment Data Services (IDS) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 5 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Mascher | H4 Operations | 3 | Allianz Technology | AZ Technology | 7 | AMOS | Allianz Technology | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 1 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Balbinot | H5 Insurance Western & Southern Europe, AZAP | 4 | AZAP | AZAP | 8 | CNPC | Allianz China - P&C | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 9 | CNH | Allianz China - Holding | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 10 | ID | Allianz Indonesia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 11 | JPLH | Allianz Japan - Life | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 12 | LAPC | Allianz Laos | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 13 | MY | Allianz Malaysia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 14 | PH | Allianz Philippine - L&H | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 15 | LK | Allianz Sri Lanka | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 16 | AS | Allianz Singapore | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 17 | TWL | Allianz Taiwan - Life | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 18 | TH | Allianz Thailand | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 19 | FIN | FinOS - Holding | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
| H2 Finance, Controlling, Risk | 5 | Allianz Benelux | Europe 2 | 21 | BLX | Allianz Benelux | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 6 | Allianz France | Europe 2 | 22 | FR | Allianz France | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 7 | Allianz Greece | Europe 3 | 23 | GR | Allianz Greece | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 8 | Allianz Italy | Europe 3 | 24 | IT | Allianz Italy | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 9 | Allianz Turkey | Europe 3 | 25 | TR | Allianz Turkey | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Theis | H7 Insurance German Speaking Countries & CEE | 10 | Allianz Germany | Europe 1 | 26 | AZD | Allianz Germany | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 11 | CEE | CEE | 27 | AT | Allianz Austria (Elementar) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 28 | BG | Allianz Bulgaria | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 29 | CZ | Allianz Czechia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 30 | HU | Allianz Hungary | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 31 | HR | Allianz Croatia (Zagreb) | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 32 | PL | Allianz Poland | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 33 | RO | Allianz Romania (Tiriac) | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 34 | RU | Allianz Russia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 35 | SK | Allianz Slovakia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 36 | UKR | Allianz Ukraine | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
| H2 Finance, Controlling, Risk | 12 | Allianz Suisse | Europe 1 | 37 | CH | Allianz Switzerland | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Hunt | H8 Asset Management, USA Life Insurance | 13 | Allianz Asset Management Holding (AAM) | Asset & Overseas | 38 | AAM | Allianz Asset Management Holding (AAM) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 15 | Allianz Global Investors (AGI) | Asset & Overseas | 39 | AGI | Allianz Global Investors (AGI) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 16 | Pacific Invest.Manag. Comp.(PIMCO) | Asset & Overseas | 40 | PIMCO | Pacific Investement Management Company (PIMCO) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 17 | Allianz Life | Asset & Overseas | 41 | USL | Allianz Life US | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 4 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Peiris | H9 Global Lines & Anglo Markets, MENA, Africa | 18 | Allianz Africa | AZ Africa | 42 | AFR | Allianz Africa | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | AZ Africa | 43 | MA | Allianz Morocco | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 2 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 19 | MENA | MENA | 44 | EGLH | Allianz Egypt L&H | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 45 | EGPC | Allianz Egypt P&C | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 46 | LB | Allianz Lebanon | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 47 | SA | Allianz Saudi Arabia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 4 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 20 | Allianz Global Corporate & Specialty (AGCS) | Europe 1 | 48 | AGCS | Allianz Global Corporate & Specialty (AGCS) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 21 | Reinsurance | Europe 1 | 49 | AZRE | Allianz Reinsurance | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 22 | Allianz Australia | Asset & Overseas | 50 | AU | Allianz Australia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 23 | Allianz Ireland | Europe 3 | 51 | IE | Allianz Ireland | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 24 | Allianz UK | Europe 3 | 52 | UK | Allianz UK | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 25 | Euler Hermes Group | Europe 2 | 53 | EH | Euler Hermes | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
.
de la Sota | H10 Business Transformation | 26 | Allianz Ibero & Latin America | IbertoLatAm | 54 | AR | Allianz Argentina | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 55 | BR | Allianz Brazil | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 56 | CO | Allianz Colombia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 57 | MX | Allianz Mexico | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 58 | PT | Allianz Portugal | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 59 | ES | Allianz Spain (Seguros) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 6 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 27 | Allianz Partners | Europe 2 | 60 | AWP | Allianz Partners | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 28 | tbd | Shared Services | 60 | AZX | AllianzX | n.a. | n.a. | [8 empty] | n.a. | n.a. | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 8 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 60 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
To be discussed: brauche wir die Übersicht-Seite. M.E. nicht unbedingt.

## Status Overview
ç | IT Security Investment Initiative
| Status overview |  | HY1 2021
# | Focus Area | # | MID | Global Security Initiative Measure | Progress KPIs | (Baseline/Target) | Measure Lead | Approved Budget | Labor | Non-Labor | Risk | Budget | Artefacts | Risk | Budget | Artefacts
1 | Slow Down Hackers | M274 | M274 | Extend currently running TIBER exercise | # of scenarios tested | (0/4) | Andreas Wagner | 1838.72 | 1838.72 | 0 |  |  |  | 0 | 0 | 0
2 | Slow Down Hackers | M275 | M275 | Cloud Security Competence Center + Secret Mgmt. | # of Security Consultations | (0/10) | Marc Bochtler | 800 | 800 | 0 |  |  |  | 0 | 0 | 0
3 | Slow Down Hackers | M 276 | M276 | Global & Scalable Application Pen Test Service Setup | # of application penetration tests performed | (0/30) | Clemens Friedrich | 950 | 890 | 60 |  |  |  | 0 | 0 | 0
4 | Slow Down Hackers | M277 | M277 | Realtime auditing & sec monitoring for Active Directory | # of event propagation from the source to the SIEM response | (0/3) | Alexander Heinze | 670 | 550 | 120 |  |  |  | 0 | 0 | 0
5 | Slow Down Hackers | M278 | M278 | IAM Password Hash Synchronization to Azure Active Directory | # of artefacts completed | (0/5) | Alexander Heinze | 448 | 448 | 0 |  |  |  | 0 | 0 | 0
6 | Slow Down Hackers | M279 | M279 | PTA (Privileged Threat Analytics) | # of artefacts achieved and requirements analyzed | (0/9) | Alexander Heinze | 670 | 550 | 120 |  |  |  | 0 | 0 | 0
| Slow Down Hackers |  | M302 | IAM Role Management & Machine Learning Analytics | # of reached milestones | (0/5) | Alexander Heinze | 811 | 751 | 60 |  |  |  | 0 | 0 | 0
7 | Increase Detection | M280 | M280 | Advanced Network-based detection and response | # of new generation ADH deployment | (0/10) | Thomas Wolf | 353 | 250 | 103 |  |  |  | 0 | 0 | 0
8 | Increase Detection | M281 | M281 | Passive DNS Monitoring & DNS Firewalling | # of DNS Server logs consumed | (0/2) | Lucas Tscherter | 337 | 210 | 127 |  |  |  | 0 | 0 | 0
9 | Increase Detection | M282_1 | M282 | Global Deception rollout | # of DCs and endpoints covered with deception | (0/6) | Lucas Tscherter | 1620 | 1350 | 270 |  |  |  | 0 | 0 | 0
10 | Increase Detection | M283 | M283 | Enhance Cloud response & Secure Allianz critical Apps | # of implemented cloud use cases | (0/10) | Lucas Tscherter | 505 | 475 | 30 |  |  |  | 0 | 0 | 0
11 | Increase Detection | M284 | M284 | SOAR Rollout and case management implementation | # of integrations or play books implemented | (0/8) | Lucas Tscherter | 690 | 610 | 80 |  |  |  | 0 | 0 | 0
12 | Increase Detection | M285 | M285 | Increase Effectiveness of Micro Segmentation and Rollout in EU | # of business critical applications moved to Enforce-Mode | (0/30) | Clemens Friedrich | 420 | 420 | 0 |  |  |  | 0 | 0 | 0
13 | Increase Detection | M286 | M286 | Build Central Dashboard to Increase Transparency and Real Time Monitoring | # of Reporting User Stories designed and User Stories implemented | (0/12) | Clemens Friedrich | 285 | 285 | 0 |  |  |  | 0 | 0 | 0
14 | Reduce Damage | M287_1 | M287 | Extension of vulnerability mgmt. to clients and global policy compliance rollout | # of OEs covered with Qualys agents on clients | (0/20) | Clemens Friedrich | 1250 | 1150 | 100 |  |  |  | 0 | 0 | 0
15 | Reduce Damage | M288 | M288 | AGN Secure Network Access and Segregation | # of reached milestones | (0/4) | Michael Kahlfuss | 588 | 538 | 50 |  |  |  | 0 | 0 | 0
16 | Reduce Damage | M289 | M289 | Acceleration of Password Manager service | # of users rolled-out to password manager service | (0/1000) | Rainer Mahlo | 350 | 350 | 0 |  |  |  | 0 | 0 | 0
17 | Reduce Damage | M290 | M290 | Re-Design Of Cloud Application Discovery Service | # of Service design documents for future CAD service developed | (0/6) | Clemens Friedrich | 155 | 155 | 0 |  |  |  | 0 | 0 | 0
18 | Reduce Damage | M291 | M291 | Privileged Access Management for Cloud | # of validate possible integrations | (0/4) | Alexander Heinze | 200 | 200 | 0 |  |  |  | 0 | 0 | 0
19 | Reduce Damage | M302 | M301 | Global Tier 0 Hosting Platform Preparation & APAC Pilot | # of Global Service AD (ADTRootdom.net & Rootdom.net Domain Controllers) extended to Tier 0 Hosting Platform in APAC # of Local APAC units of Allianz Partners: Domain Controllers onboarded to Tier 0 Hosting Platform | (0/8) (0/4) | Alexander Heinze | 1000 | 750 | 250 |  |  |  | 0 | 0 | 0
20 | Streamline Compliance |  | M292 | Double Key Encryption / Extended Security & Compliance for M365 | # of reached artefacts | (0/5) | Julian Bönigk | 750 | 690 | 60 |  |  |  | 0 | 0 | 0
21 | Streamline Compliance | M293 | M293 | Automated Toxic Tracking for Client-based Assets | # of Toxic Asset Dashboard including client IT asset data (e.g. AVC, AMC, fat client, smart mobile de-vices) for minimum of 25 OEs | (0/25) | Benjamin Warnholz | 360 | 300 | 60 |  |  |  | 0 | 0 | 0
22 | Streamline Compliance | M294 | M294 | Integrated Information Risk Management early Live​ | # of reached milestones | (0/5) | Michael Habel | 650 | 650 | 0 |  |  |  | 0 | 0 | 0
23 | Streamline Compliance | M295 | M295 | Global Security Platform GITSO blueprint | # of KPI + SLA vetting draft for 6 Security Services | (0/12) | George Dietrichsbruckner | 300 | 298 | 2 |  |  |  | 0 | 0 | 0
24 | Build Security Organization / Skills | M296 | M296 | Financial Loss Quantification | # of OEs evaluated within BitSight financial model | (0/10) | Thomas Thuspass | 400 | 400 | 0 |  |  |  | 0 | 0 | 0
25 | Build Security Organization / Skills | M297 | M297 | Measure and Enhance Global Phishing Resilience | # of learning nuggets and OE dashboards created | (0/10) | Clemens Friedrich | 995 | 720 | 275 |  |  |  | 0 | 0 | 0
26 | Build Security Organization / Skills | M298 | M298 | Strategic THREAT Intelligence and Resulting risk Identification Program | # of reached artefacts | (0/3) | Thomas Wolf | 480 | 480 | 0 |  |  |  | 0 | 0 | 0
27 | Build Security Organization / Skills | M299_1 | M299 | Enforcement of Security Architecture | # of architectural documents (e.g. pattern / analysis / methodology) published | (0/7) | Jan General | 430 | 430 | 0 |  |  |  | 0 | 0 | 0
28 | Build Security Organization / Skills | M300 | M300 | Metrics phase @We protect scale up on skills | # of high qualitative metrics for ROI | (0/5) | Samuel Hurst | 540 | 390 | 150 |  |  |  | 1 | 0 | 1

## M274
M274 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Extend currently running TIBER exercise |  |  | Slow Down Hackers |  |  |  |  | Andreas Wagner |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1.839k€ |  | Spent (as per 03.09.2021) |  |  |  | 178k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 1839k€ |  | Budget (labor) |  |  |  | 178k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 25%
75%
0%
1 | Conduct TIBER execution for the OEs |  |  | 25% |  | 829k€ | TI report feedbacked, Test plan draft available | [6 empty] | Finalize TI report & Test plan | [7 empty] | 100%
0%
100%
2 | Coordinate wrap-up / test closure |  |  | 0% |  | 410k€ | [15 empty] | 0%
100%
0%
3 | Execute Post-findings-review |  |  | 0% |  | 300k€ | [15 empty] | 100%
4 | Plan & start finding Remediation |  |  | 0% |  | 300k€
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of scenarios tested (0/4)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M275
M275 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Cloud Security Competence Center + Secret Mgmt. |  |  | Slow Down Hackers |  |  |  |  | Marc Bochtler |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 800k€ |  | Spent (as per 03.09.2021) |  |  |  | 155k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 800k€ |  | Budget (labor) |  |  |  | 155k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 40%
60%
15%
1 | Extend feature set of already available security features in Prisma Cloud platform (specifically onboarded serverless functions) |  |  | 40% |  | 200k€ | Serverless functions enabled. | [6 empty] | Rollout to customers has to be done. | [7 empty] | 85%
15%
85%
2 | Cover capacity challenges in Cloud Security Competence Center ramp up (Funding, hiring) |  |  | 15% |  | 200k€ | 3 external ressources (as in 1 HY measure) hired and funded. | [6 empty] | Alignment where the Cloud Security Competence Center will be allocated has to be executed. | [7 empty] | 0%
100%
0%
3 | Design secret management service for cloud native applications (not limited to TLS) |  |  | 15% |  | 200k€ | Some options for final architectural decision identified (Co-located vs standalone, options for Vault cluster built (Virtual Machines vs Kubernetes)) | [6 empty] | Shaping and reviewing the options for the final architectural decision.Review of architectural flows. Finale decison to be done. | [7 empty] | 100%
4 | Perform POC of the HashiCorp Vault implementation and integration readiness for two usecases |  |  | 0% |  | 200k€ | [7 empty] | Secret management service has to be designed first.
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of Security Consultations (0/10)
2 | (/)
On track
Actions required
Management attention required
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M276
M276 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Global & Scalable Application Pen Test Service Setup |  |  | Slow Down Hackers |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 950k€ |  | Spent (as per 03.09.2021) |  |  |  | 317k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 890k€ |  | Budget (labor) |  |  |  | 317k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 60k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 40%
60%
40%
1 | Establish the Application Penetration Testing service offering (SPM Process) |  |  | 40% |  | 130k€ | - Further SNOW Integration: Agree technical details and API to connect SNOW to Pentest Vendors | [6 empty] | - Further SNOW Integration: Discussion on implementation of technical details and API to connect SNOW to Pentest Vendors | [7 empty] | 60%
25%
75%
2 | Finalize design & integration of the service in the Allianz ecosystem incl. reporting capabilities |  |  | 40% |  | 110k€ | - Agree Technical Details of Data Exchange between Archer and Splunk - Finalize API Description for Vendors | [6 empty] | - Implementation of Connection between Archer and Splunk - Discussion Connection of Providers to Splunk - Provisioning of Access to Splunk for Application Owner | [7 empty] | 55%
45%
15%
3 | Set-up of the technical pen-test factory (‘Hack Lab’) |  |  | 25% |  | 350k€ | - Setup Hacklabs for first wave of penests - Develop IT Architecture for final IPT Service- Upgrade IT-Infrastructure (IP-Range) | [6 empty] | - Prepare ITFAM TRB Presenatation - Update IT Architecture also with Splunk and Archer - Provisioning of Hacklabs for next tests | [7 empty] | 85%
4 | Contracting of external partners and establish provider management |  |  | 55% |  | 70k€ | - Contracts with EY and Deloitte are closed - PO has been created on AZ Tech side and sent to both vendors - Onboarding of testers is ongoing | [6 empty] | - Establish standardised planning process and vendor management; - Establishing of a rolling test planning
5 | Perform penetration tests to ramp-up the service offering |  |  | 15% |  | 430k€ | - Calls with first ISOs and App Owner performed - First Questionnaires have been collected and sent to vendors for preparation - Organise Scoping Calls and start first test wave | [6 empty] | - Identify new Apps to be tested, to make sure at least 30 apps can be testes until end of the year - Organise Scoping Calls and start second test wave
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | Risk of not achieving KPI by end of the year due to missing applications and commitment for Pen-Testing |  |  |  |  | Low |  | Start of a campaing to attract more ISOs and App Owner; Get Management Suppot for this campaing. Campaing must start during September, to still take effect in 2021 |  |  |  |  | 2021-09-30
1 | # of application penetration tests performed (1/30)
2 | (/)
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M277
M277 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Realtime auditing & sec monitoring for Active Directory |  |  | Slow Down Hackers |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 670k€ |  | Spent (as per 03.09.2021) |  |  |  | 223k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 550k€ |  | Budget (labor) |  |  |  | 223k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 120k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 10%
90%
7%
1 | Identification of requirements for the solution and scope definition (.docx) |  |  | 10% |  | 100k€ | - Requirement gathering phase (completed to 30%) - Requirement consolidation (completed to 11%) | [6 empty] | - Requirement confirmation by the stakeholders | [7 empty] | 93%
0%
100%
2 | Implementation of realtime audit and monitoring for pilot AD/AAD with the N3K Cygna Auditor solution (.docx) |  |  | 7% |  | 160k€ | - Initial Workshop and alignmentm with N3K - Gathering of pre-implementation documentation for Cygna (completed to 50%) | [6 empty] | - Implementation of Cygna on pilot scope - Event forwarding to SIEM - Consolidation with stakeholders | [7 empty] | 5%
95%
10%
3 | Requirement fulfilment analysis, that includes a validation of the capabilities of the implemented solution (.docx) |  |  | 0% |  | 130k€ | [7 empty] | - Fullfulment analysis - Alignment with vendor - Alignment with stakeholders | [7 empty] | 90%
4 | High-Level integration concept, Roadmap and effort estimation for an integration into the ACDC landscape (.docx) |  |  | 5% |  | 200k€ | - High level concept | [6 empty] | - Low level concept - SIEM integration roadmap + effoert estimation - Alignment with stakeholders
5 | Peer-group comparison of Cygna (.docx) |  |  | 10% |  | 80k€ | - Supplier identification (100% completed) | [6 empty] | - Supplier comissioning - Consolidation of results
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of event propagation from the source to the SIEM response (0/3)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
Management attention required
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M278
M278 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
IAM Password Hash Synchronization to Azure Active Directory |  |  | Slow Down Hackers |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 448k€ |  | Spent (as per 03.09.2021) |  |  |  | 149k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 448k€ |  | Budget (labor) |  |  |  | 149k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 30%
70%
30%
1 | Conceptualization, high-level and low-level design for password hash synchronization (.docx) |  |  | 30% |  | € 75 k | - High-level design initiated -Requiremnet (scope) are initiated | [6 empty] | - Signoff from low-level design -Stakeholder to approve the requirements (scope) | [7 empty] | 70%
50%
50%
2 | Design for Microsoft Identity Protection (MIP) and integration architecture to ACDC (.ppt) |  |  | 30% |  | € 75 k | - High-level design initiated -Requiremnet (scope) are initiated | [6 empty] | - Signoff from high-level design | [7 empty] | 15%
85%
1%
3 | Proof of Concept (PoC) implementation of password hash synchronization for Pilot OE |  |  | 50% |  | € 200 k | - Activate password hashing for AZ CH in ADT environment - Move to Production | [6 empty] | - Password Hashing has been activated and sync with Switzerland - Configuration PHS is sync - Capabilities of use of custom attribute is supported but not recommended by MS - Password hashing change and synchronise with the password id happen every 2 minutes | [7 empty] | 99%
4 | Initiation of ACDC use-case for credential abuse alerts from MIP to ACDC (.docx) |  |  | 15% |  | € 50 k | -Use case ACDC send to the ACDC team | [6 empty] | -Feedback and signoff of the use case
5 | Creation of sample reporting (via MIP tool) |  |  | 1% |  | € 48 k | Ms.team have to suggest a solution | [6 empty] | Start the discussion with Ms.team
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of artefacts completed (0/5)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M279
M279 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
PTA (Privileged Threat Analytics) |  |  | Slow Down Hackers |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 670k€ |  | Spent (as per 03.09.2021) |  |  |  | 223k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 550k€ |  | Budget (labor) |  |  |  | 223k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 120k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 100%
0%
50%
1 | Requirement identification and usecase definition |  |  | 100% |  | € 55 k | Requirments identifed and approved by internal team Usecases identified, aligned with GPAM and ACDC | [6 empty] | Final adjustments to requirments and usecases | [7 empty] | 50%
25%
75%
2 | Vendors evaluation and selection |  |  | 50% |  | € 80 k | Workshops with potential vendors scheduled Going forward for POC with CyberArk | [6 empty] | Evaluation of vendors capabilities based on the information to be gathered at workshops | [7 empty] | 15%
85%
0%
3 | Architectural design and technical suitability analysis |  |  | 25% |  | € 145 k | High level design is ready, proceeding to more granular low level design | [6 empty] | To start with low level design and asking for approval | [7 empty] | 100%
4 | POC implementation and features testing |  |  | 15% |  | € 155 k | Requirments for PoC identified Requirments are communciated to respective teams for implementation | [6 empty] | Getting required infrastrature in place (Mid oct) Getting the actual PoC in place
5 | Evaluation of integration with SIEM and events analysis |  |  | 0% |  | € 115 k
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of artefacts achieved and requirements analyzed (1/9)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M302
M302 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
IAM Role Management & Machine Learning Analytics |  |  | Slow Down Hackers |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 811k€ |  | Spent (as per 03.09.2021) |  |  |  | 270k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 751k€ |  | Budget (labor) |  |  |  | 270k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 60k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 0%
100%
0%
1 | Concept of Role Management and Role Governance including integration architecture to GIAM |  |  | 0% |  | 75k€ | [7 empty] | In contract negotiation with Accenture | [7 empty] | 100%
0%
100%
2 | Automation concept in the context of access management (confidence rating definition) |  |  | 0% |  | 75k€ | [15 empty] | 0%
100%
0%
3 | Pilot Installation in AZ Technology or AZ SE with integration to GIAM; Focus on five critical systems (rootdom.net Active Directory, PKI, SAP, VPN, TBD) |  |  | 0% |  | 300k€ | [7 empty] | Hardware orderung for necessary infrastructure Clarfication pilot licenses with ForgeRock | [7 empty] | 100%
4 | Showcase: (1) a regulator and audit compliant reporting capability (2) the benefits of integrating technical role management with organizational and business role management. |  |  | 0% |  | 150k€
5 | Design Role Management Service – i.e. high-level use cases and related RACI between OEs and AZT |  |  | 0% |  | 150k€
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | Contracting & onboarding with Accenture |  |  |  |  | Medium |  | Negotiation of contract with procurement Involvement of senior management |  |  |  |  | 2021-09-15
1 | # of reached milestones (0/5)
2 | (/)
|  |  | Artefact Risk |  | Hardware not available in time |  |  |  |  | Medium |  | detailing hardware requirement with HMO |  |  |  |  | 2021-09-15
On track
Actions required
|  | Management attention required | General Risk |  | Liscense cost for pilot with Forgerock |  |  |  |  | Medium |  | Striong discussionn with Forgerock Involvement of senior management if necessary |  |  |  |  | 2021-09-20
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M280
M280 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Advanced Network-based detection and response |  |  | Increase Detection |  |  |  |  | Thomas Wolf |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 353k€ |  | Spent (as per 03.09.2021) |  |  |  | 0k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 250k€ |  | Budget (labor) |  |  |  | 0k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 103k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 5%
95%
5%
1 | Connection between Cynet and ADH Edge Node |  |  | 5% |  | € 85 k | Kickoff performed Strategy aligned POCs defined DCSO | [6 empty] | Clarify Cynet requirements Provide ADH interface Create / Test connection, rollout, documentation | [7 empty] | 95%
5%
95%
2 | Deployment new ADH generation |  |  | 5% |  | € 60 k | Kickoff performed Strategy aligned DCSO offer and SoW provided in draft version | [6 empty] | Offer and SoW finalization and approval Creation of rollout plan, creation of documentation Execution of roolout plan, finalization of documentation | [7 empty] | 5%
95%
0%
3 | Integrated ACDC Infrastructure and processes |  |  | 5% |  | € 70 k | Kickoff performed Proof of Value criteria aligned SPOC defined ACDC | [6 empty] | ACDC internal alignment PoV execution and comparison with other vendor/approach Detail planning, execution and documentation | [7 empty] | 100%
4 | ADH connection to Cynet central endpoint data repositories established |  |  | 5% |  | € 35 k | Kickoff performed Strategy aligned SPOC defined Cynet | [6 empty] | Clarify DCSO / ADH requirements Provide Cynet interface Create / Test connection, rollout, documentation
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of new generation ADH deployment (0/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M281
M281 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Passive DNS Monitoring & DNS Firewalling |  |  | Increase Detection |  |  |  |  | Lucas Tscherter |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 337k€ |  | Spent (as per 03.09.2021) |  |  |  | 6k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 210k€ |  | Budget (labor) |  |  |  | 6k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 127k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 20%
80%
15%
1 | Creation of logging and analytics architecture and implementation |  |  | 20% |  | € 80 k | DNS architecture analysis has been generally done with only couple of points to clarify. | [6 empty] | Next steps for DNS team (deploying DNS tap and converting DNS query logs into JSON format) has been agreed on. | [7 empty] | 85%
10%
90%
2 | Connection of PoC DNS servers and creation/testing of use-cases |  |  | 15% |  | € 100 k | Ealuation of use cases started. First ideas drafted. Next steps for DNS team (deploying DNS tap and converting DNS query logs into JSON format) has been agreed on. | [6 empty] | Establsih connection to DNS servers and continou alignment on use cases. | [7 empty] | 0%
100%
0%
3 | DNS Sinkholing requirements and vendor discovery |  |  | 10% |  | € 30 k | Aligned to implement sinkholin internally. | [6 empty] | Further detailing of sinkholin solution. | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of DNS Server logs consumed (0/2)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M282
M282 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Global Deception rollout |  |  | Increase Detection |  |  |  |  | Lucas Tscherter |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1620k€ |  | Spent (as per 03.09.2021) |  |  |  | 281k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 1350k€ |  | Budget (labor) |  |  |  | 281k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 270k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 35%
65%
25%
1 | Setup Deception infrastructure incl. rollout to Asia Pacific and North American DCs (AP1 & AP2 and NA1 & NA2) |  |  | 35% |  | € 560 k | Hardware procurement approved​ IP addresses for hardware reserverd​ Cable Matrix AP1 & AP2 completed | [6 empty] | IP address reservation in progress​ Cabling procurement for AP1 in progress, AP2 quote approved Alignment with Data Center Teams | [7 empty] | 75%
10%
90%
2 | Cover FMO & CMP servers and AVC clients in AP1 & AP2 and NA1 & NA2 datacenters |  |  | 25% |  | € 600 k | Windows, Linux, AVC teams contacted and alignment started | [6 empty] | Project plan refinement for endpoint coverage ongoing Scope review (centrally vs. regionally managed servers) | [7 empty] | 10%
90%
0%
3 | Conduct ADC Public Cloud Pilot |  |  | 10% |  | € 115 k | Initial alignment started | [6 empty] | Cloud alignment with vendor, alignment with Patrick Zeitz mid/end September | [7 empty] | 100%
4 | ACDC SOAR Integration |  |  | 10% |  | € 75 k | Initial alignment done. | [6 empty] | Start planned after architecture approval and hardware ordering
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of DCs and endpoints covered with deception (0/6)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M283
M283 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Enhance Cloud response & Secure Allianz critical Apps |  |  | Increase Detection |  |  |  |  | Lucas Tscherter |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 505k€ |  | Spent (as per 03.09.2021) |  |  |  | 41k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 475k€ |  | Budget (labor) |  |  |  | 41k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 30k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 25%
75%
20%
1 | Develop, implement and document Cloud Use Cases |  |  | 25% |  | € 110 k | MS onboarding complete​ First analysis of potential use cases completed by MS S3 bucket use case implemented | [6 empty] | ACDC to align and prioritize use cases​ S3 use cases variations to be implemented | [7 empty] | 80%
20%
80%
2 | Create new and updated incident response run books for Cloud log sources |  |  | 20% |  | € 75 k | S3 bucket run book developed | [6 empty] | Further alignment and implementation off required run books | [7 empty] | 35%
65%
0%
3 | Review and fine tune the Cloud SIEM Sentinel |  |  | 20% |  | € 75 k | MS engineers finished analysis of existing Sentinel setup | [6 empty] | MS to review and propose retention options for Sentinel logs (hot/cold standby for 12 months) | [7 empty] | 100%
4 | Identify most security related events/information in Allianz business critical applications |  |  | 35% |  | € 110 k | AdoIT list and ARA list merged​ Alignment with ACDC on partly onboarded applications like SAP Questionaire sent out to group 1 of prio applications | [6 empty] | Collect, analyze and process questionaire feedback
5 | Prepare SIEM onboarding of identified business critical applications |  |  | 0% |  | € 105 k | Not yet started
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of implemented cloud use cases (1/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M284
M284 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
SOAR Rollout and case management implementation |  |  | Increase Detection |  |  |  |  | Lucas Tscherter |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 690k€ |  | Spent (as per 03.09.2021) |  |  |  | 44k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 610k€ |  | Budget (labor) |  |  |  | 44k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 80k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 40%
60%
30%
1 | Implement SOAR integrations and play books |  |  | 40% |  | € 300 k | First set of integrations implemented Implementation continuing | [6 empty] | Additional playbooks in acceptance testing by the users​ Alignment on mail integration ongoing | [7 empty] | 70%
35%
65%
2 | Drive the shift from Incident to Case Management |  |  | 30% |  | € 140 k | Rough draft of the documentation for the follow-up workshop in September completed. | [6 empty] | Follow-Up Workshop on 22.09.2021 to present the initial draft for feedback by the ACDC team | [7 empty] | 0%
100%
0%
3 | Increase user adoption of SOAR within ACDC and onboard local security teams through trainings and guided use case development |  |  | 35% |  | € 170 k | Preliminary accounts created and a “welcome” email template prepared part of the initial contact with the users | [6 empty] | Finalize initial training concept with the ACDC SOAR team | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target)
1 | # of integrations or play books implemented (4/8)
2 | (/)
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M285
M285 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Increase Effectiveness of Micro Segmentation and Rollout in EU |  |  | Increase Detection |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 420k€ |  | Spent (as per 03.09.2021) |  |  |  | 31k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 420k€ |  | Budget (labor) |  |  |  | 31k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 15%
85%
20%
1 | Move 30 business critical applications from Build- to Enforce-Mode and develop a standardized process |  |  | 15% |  | € 205 k | - AZ MO - Second app enforced - AZ UK - Discussions around Enforcement progressing, PoC to include full Operating Model - AZ Czech - Test enfironment of first app enforced, Timeline agreed for Production and other apps - AZ AU, AZ SK & AZ HU - Work on Rulesets progressing - AZ FR - Work on technical rules started - First version of Move-To-Enforce-Process created and documented | [6 empty] | - AZ MO - Plan enforcement for upcoming apps - AZ UK - Progress & finalize the enforcement PoC ​ - AZ CZ – Enforce Prod-Environment + other apps​ - AZ AU, AZ HU & AZ SK - Progress & finalize Enforcement​ - AZ FR – Continue work on technical rules - AZ PL – Move to Policy Creation Phase​ | [7 empty] | 80%
45%
55%
2 | Onboarding of additional 25 business critical applications to AMS in Europe |  |  | 20% |  | € 145 k | - AZ Reinsurance – Additional demand identify​ - AZ Suisse – First test server onboarded - AZ MO - Onboarding Template for first additional app received - AGCS - Discussion progressing with new SPOC - AZ Partners - Discussion progressing with new SPOC - 5 Applications onboarded | [6 empty] | - AZ Tech – Plan and progress ContactCenter​ - AZ Suisse – Perform tests and plan further onboarding - AZ Reinsurance – Clarify scope and start planning​ - AGCS - Continue alignment - AZ Partners - Continue alignment | [7 empty] | 0%
100%
0%
3 | Finalize SNOW- and AdoIT-Integration to improve operational processes and governance |  |  | 45% |  | € 70 k | - SNOW-Integration: Orchestra not needed, direct interface with SNOW instead, needed Attributes provided, Interface and Technical User in creation, Reporting possible via Grouping Elements - AdoIT-Integration: First apps linked | [6 empty] | - Prepare Dev-Sever & Start Developing as soon as Interface and TU are ready - Finalize App Linking in AdoIT - Finalize Reporting-Model once all apps are linked | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of business critical applications moved to Enforce-Mode (2/30)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M286
M286 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Build Central Dashboard to Increase Transparency and Real Time Monitoring |  |  | Increase Detection |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 285k€ |  | Spent (as per 03.09.2021) |  |  |  | 8k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 285k€ |  | Budget (labor) |  |  |  | 8k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 33%
67%
5%
1 | Development of 6 Real Time Reporting User Stories based on selected sensors |  |  | 33% |  | 100k€ | Combined Architecture Design continued with eGRC / Archer Team Detailed measure plan improved; alignment ongoing User stories prioritized by sensor with Measure Sponsor | [6 empty] | Create and approve 6 user stories Create architecture and implementation concept Dashboard Visualization Concept RACI Matrix for app usage | [7 empty] | 95%
3%
97%
2 | Implementation of data delivery towards Governance & Control Dashboard |  |  | 5% |  | € 60 k | Tests with time series data lakefor historic data views, Access to API and MySQL getting along Meetings with Sensor Owners initiated (SIEM, Cynet, more to follow) Access to sensor data lake requested | [6 empty] | API implementation towards User Interface Sensor Access available Backend extended and Source Code delivered | [7 empty] | 0%
100%
0%
3 | Development of 6 Reporting Dashboards based on defined User Stories |  |  | 3% |  | € 125 k | Presented current front-end implementation to new measure members Updated existing prototype data (“under the hood”) to prepare for results from WP2 | [6 empty] | 6 User Stories implemented in Front-End SSO integrated Friendly User Test Source Code and Documentation | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of Reporting User Stories designed and User Stories implemented (1/12)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M287
M287 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Extension of vulnerability mgmt. to clients and global policy compliance rollout |  |  | Reduce Damage |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1250k€ |  | Spent (as per 03.09.2021) |  |  |  | 253k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 1150k€ |  | Budget (labor) |  |  |  | 253k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 100k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 70%
30%
35%
1 | Extension of AVM Scope to cover clients |  |  | 70% |  | € 150 k | Scripts and data models have been adjusted. Data for client vulnerabilities is flowing into Splunk now. | [6 empty] | Prototype dashboard to be created for Pilot Oes Croatia and Ireland. After that testing can be done. | [7 empty] | 65%
45%
55%
2 | Rollout of the Qualys Agent to clients in 20 OEs to enable Vulnerability Scanning |  |  | 35% |  | € 570 k | Commitment of 20+ OEs received for Qualys Agent Rollout on Clients Deployment within CEE and APAC ongoing Deployment on AMC ongoing | [6 empty] | Kick-off session for further OEs Align on global AVC approach (Standard AZ Tech Image & BYOI Solutions) | [7 empty] | 20%
80%
20%
3 | Enable OS Level Policy Compliance scanning & reporting on 10.000 FMO & HC servers |  |  | 45% |  | € 260 k | GPAM solution for Linux and WIN tested successfully PC activation done for 4500 HC servers | [6 empty] | Activation for FMO NA ongoing (GPAM solution in place) Start activation for FMO E1/E2 Communication towards more than 20 OEs for PC activation ongoing | [7 empty] | 80%
4 | Develop proposal and concept for tool-based remediation tracking process |  |  | 20% |  | € 90 k | First alignments done and prerequisites defined | [6 empty] | Clarification if CMDB quality for local assets is sufficient Clarification if Qualys API is working fine Clarification of license costs
5 | Creation of documentation for definition of AVM Scope (Cloud Agents / Policy Compliance) as a Class 1 Standard |  |  | 20% |  | € 80 k | First alignements and expectation management done | [6 empty] | Clarification of current status (AVM class 1 standard?) General decision if class 1 standardized will provide benefit
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of OEs covered with Qualys agents on clients (1/20)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M288
M288 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
AGN Secure Network Access and Segregation |  |  | Reduce Damage |  |  |  |  | Michael Kahlfuss |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 588k€ |  | Spent (as per 03.09.2021) |  |  |  | 196k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 538k€ |  | Budget (labor) |  |  |  | 196k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 50k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 15%
85%
0%
1 | Finalizes the current NAC concept for Network Access Control |  |  | 15% |  | € 124,8 k | - First workshops started to define the onboarding process for AMC and printer to 802.1X - Receive feedback on the printers in Ireland (which models are 802.1x capable) | [6 empty] | - Sup-PKI mus be setup - AMC configuration for 802.1X must be discussed with the vendor - discuss the other devices with ISO Ireland | [7 empty] | 100%
15%
85%
2 | Support from Accenture and Cisco to work on the concept and the implementation strategy |  |  | 0% |  | € 288 k | - ODM is created and the scope is aligned with Accenture | [6 empty] | - Accenture now has to deliver the offer (for voice and video endpoints) - Service contract with Cisco must be agreed | [7 empty] | 10%
90%
0%
3 | Run and test implementation for a pilot site |  |  | 15% |  | € 62,4 k | - LAN test eqipiment available - 802.1x configuration tested with printer | [6 empty] | - Get various device classes for the test environment - Plan the test of AGN telephones and video endpoints with Accenture | [7 empty] | 100%
4 | Preparation, Planning and Go-Live for 1 x OE |  |  | 10% |  | € 62,4 k | - Scope discussed in detail with the Irish colleagues and feedback was received on the locally operated printers with regard to 802.1x capability. | [6 empty] | - Plan a meeting with ISO Ireland to discuss and finalize further configurations
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | Availability of internal resources (AMC, PKI); these are also required by other projects |  |  |  |  | Medium |  | Define substitutions so that there is no bottleneck |  |  |  |  | 2021-09-30
1 | # of reached milestones (1/4)
2 | (/)
|  |  | General Risk |  | Slow progress on the ODM delays the implementation of the voice and video endpoints |  |  |  |  | Medium |  | Escalation via Stefano Fabbri to expedite delivery Accenture is able to support us to start with pilot activities to save on time until formal offer submission |  |  |  |  | 2021-09-15
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint
Create Powerpoint

## M289
M289 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Acceleration of Password Manager service |  |  | Reduce Damage |  |  |  |  | Rainer Mahlo |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 350k€ |  | Spent (as per 03.09.2021) |  |  |  | 117k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 350k€ |  | Budget (labor) |  |  |  | 117k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 50%
50%
50%
1 | Completion of the Testing Phase with System Integration Test |  |  | 50% |  | € 90 k | - 1st PoC with LastPass is done - 2nd PoC with Keeper is done. >50 test users in Keeper user test | [6 empty] | - Analyze the results from the Keeper PoC - Preparation of the documents to make the vendor decision | [7 empty] | 50%
25%
75%
2 | Vendor Selection and Contracting with Vendor |  |  | 50% |  | € 15 k | - Finalized vendor evaluation based on Allianz requirements | [6 empty] | - Final vendor comparison to meet the vendor decision - Negotiate and conclude a contract | [7 empty] | 25%
75%
0%
3 | Service Creation to enable the solution for the OE’s |  |  | 25% |  | € 120 k | - BSE Process completed; CITRA Process completed | [6 empty] | - Completion SPM-Process - Technical integration in SNOW | [7 empty] | 100%
4 | Technical Integration and Roll-out |  |  | 25% |  | € 125 k | - Project internal test to integrate Veridium as a MFA solution - LastPass ergonomics eval. is done; Keeper initial ergonomics eval. is done; Plan for resolving open items received from both vendors | [6 empty] | - Completion of the target solution design - Completion of the rollout planning - Workers council approval
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | New device detection on pooled VDI environment (AVC) |  |  |  |  | High |  | User Test in Q3 |  |  |  |  | 2021-12-31
1 | # of users rolled-out to password manager service (0/1000)
2 | (/)
|  |  | General Risk |  | Solutions’ ability to fulfill AZ requirements |  |  |  |  | High |  | User Test in Q3; Ergonomics Test in Q4 |  |  |  |  | 2021-12-31
On track
Actions required
|  | Management attention required | Artefact Risk |  | Resources to support with POC technical set-up & initial launch in production |  |  |  |  | Medium |  | APM support needed for SW package deployment |  |  |  |  | 2021-12-31
|  |  | Artefact Risk |  | To comply with stakeholder requirements Veridium should be available on Azure as an MFA solution |  |  |  |  | Medium |  | Intermediate MasterPassword approach with vendor MFA instead of Azure integration |  |  |  |  | 2021-09-30
|  |  | Budget Risk |  | Vendor set minimum number of users for purchase order |  |  |  |  | Medium | [6 empty] | 2021-09-30
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M290
M290 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | No |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Re-Design Of Cloud Application Discovery Service |  |  | Reduce Damage |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 155k€ |  | Spent (as per 03.09.2021) |  |  |  | 52k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 155k€ |  | Budget (labor) |  |  |  | 52k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 100%
0%
33%
1 | Development of technical & business needs and constraints |  |  | 100% |  | € 50 k | Interview with OE, H4 and AzTech performed and requirenments documentes. | [14 empty] | 67%
100%
0%
2 | Development of future service design of CAD service |  |  | 33% |  | € 65 k | Review of current Service description. Documented UseCases | [6 empty] | Discuss usecases with CAD service owner to determin which to add to revised CAD service Discuss Use Cases with AzTech | [7 empty] | 0%
100%
0%
3 | Design of interim-solution for 2022 |  |  | 100% |  | € 40 k | Approvach defined, deliverable aligned with AzTech | [14 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | formal pricing response for prefered interim solution was higher than initial quote communicated by CSAB vendors to AzTech |  |  |  |  | Low |  | - further discussion with CSAB vendors - determin alternative vendor
1 | # of Service design documents for future CAD service developed (4/6)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M291
M291 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Privileged Access Management for Cloud |  |  | Reduce Damage |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 200k€ |  | Spent (as per 03.09.2021) |  |  |  | 67k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 200k€ |  | Budget (labor) |  |  |  | 67k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 15%
85%
0%
1 | Design a concept for privileged access management solution for cloud |  |  | 15% |  | € 67 k | Workshop to collect Use Cases executed. | [6 empty] | Alignment how the architecure should look like. | [7 empty] | 100%
0%
100%
2 | Implement a POC for the privileged access management for selected accounts on Azure, AWS and databases |  |  | 0% |  | € 67 k | [7 empty] | Implementing of POC has to be planned. | [7 empty] | 0%
100%
0%
3 | Create a proposal to implement the solution as a standard service |  |  | 0% |  | € 66 k | [7 empty] | Creating of a proposal has to be planned. | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | Lack of adequate resource support , e.g. internal experts due to the amount of projects and operational involvement. |  |  |  |  | Low |  | Management awareness and commitment of internal ressources |  |  |  |  | End of September 2021
1 | # of validate possible integrations (0/4)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M301
M301 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Global Tier 0 Hosting Platform Preparation & APAC Pilot |  |  | Reduce Damage |  |  |  |  | Alexander Heinze |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 1000k€ |  | Spent (as per 03.09.2021) |  |  |  | 333k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 750k€ |  | Budget (labor) |  |  |  | 333k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 250k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 10%
90%
5%
1 | Global architecture reviewed and readjusted to latest conditions |  |  | 10% |  | € 50 k | Integration strategy reviewed & approved for WSUS (Windows Patches) and WEF (event forwarding to ArcSight) servers | [6 empty] | Onboarding of MSFT technical consultant (week 40) Final approval of Microsoft contract | [7 empty] | 95%
0%
100%
2 | Tier 0 Hosting Platform Implemented in APAC (AP1 & AP2 datacenter) |  |  | 5% |  | € 375 k | Network design and communication matrix reviewed by MSFT & created AP2 (Sidney) servers shipped (10.9.), expected delivery 28.9. AP1 (Singapore) servers' shipment planned (24.9.); del. exp. 5.10. | [6 empty] | Execution & testing of FCC (already started/ongoing) Onboarding of MSFT technical consultant (week 40) Final approval of Microsoft contract | [7 empty] | 5%
95%
0%
3 | APAC Pilot Implemented |  |  | 0% |  | € 155 k | not yet started (dependency on artefacts 1 and 3) | [6 empty] | n/a | [7 empty] | 100%
4 | Concept for Service Extension to Fully Managed Model (PaaS/SaaS) Designed |  |  | 5% |  | € 125 k | Rough solution approach and timeline developed Corresponding alignment meeting series scheduled | [6 empty] | Activities will continue in week 38 (due to vacation)
5 | Effective and streamlined liaison with local AD administrators established |  |  | 0% |  | € 45 k | not yet started | [6 empty] | n/a
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | Extended server hardware delivery times due to global semiconductor shortage may impact project timeline |  |  |  |  | Low |  | Close alignment established with Lenovo global account mgt. to speed up manufacturing of servers and delivery to AP1 and AP2 |  |  |  |  | 2021-09-30
1 | # of Global Tier 0 Hosting Platform Design and APAC Pilot (0/8)
2 | # of Local APAC units of Allianz Partners: Domain Controllers onboarded to Tier 0 Hosting Platform (0/4)
|  |  | Artefact Risk |  | Concepts for MDT server (VM deployment) and HGS service (VM encryption) may need update due to recent technical conditions. May influence timeline due to dependencies. |  |  |  |  | Low |  | Microsoft is already aware of risk(s) and checking on technical options. |  |  |  |  | 2021-09-30
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M292
M292 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Double Key Encryption / Extended Security & Compliance for M365 |  |  | Streamline Compliance |  |  |  |  | Julian Bönigk |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 750k€ |  | Spent (as per 03.09.2021) |  |  |  | 160k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 690k€ |  | Budget (labor) |  |  |  | 160k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 60k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 70%
30%
90%
1 | Documented and approved service design |  |  | 70% |  | € 120 k | High Level Service Design approved NBM approved Demand survey conducted, service price defined, incl. material number | [6 empty] | Finish 3 more SPM approvals Hand in SPM fine level design | [7 empty] | 10%
30%
70%
2 | Data privacy and security assessments done |  |  | 90% |  | € 100 k | PIA approved. ARA signed for 2021 by ISO Creation of BCM documentation | [6 empty] | Finalize SSS Add DKE to ARA | [7 empty] | 30%
70%
50%
3 | DLP configuration defined for MS Teams, SPO, OD4B |  |  | 30% |  | € 100 k | Technical evaluation of communication DLP for MS Teams done, core team testing ongoing | [6 empty] | Assess technical possibilities for MS Teams, SPO, OD4B Reconsider active DLP blocking in policies, evaluate OE-specific possibilities for policies & reporting | [7 empty] | 50%
4 | Enhanced MIP features prepared in production according to final service design |  |  | 30% |  | € 200 k | Kick-off DKE PoC on AMC. Discussions about Office ProPlus "Device Based License". | [6 empty] | Validate when O365 ProPlus will be rolled out on AVC Perform testing on AMC and resolve operational issues Prepare production implementation
5 | Enhanced document management features available in production |  |  | 50% |  | € 230 k | Define SPO site design that is in-line with ASIDM, AGCS feedback sessions conducted, price negotiation with Harmon.ie finalized & packaging initiated | [6 empty] | Finalize user testing, make SPO site design & retention / record labels and Harmon.ie available in production
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | Office 365 ProPlus will not be rolled out on AVC in HY2 2021 |  |  |  |  | High |  | Actively support AVC team, track progress of implementation |  |  |  |  | 2021-12-31
1 | # of reached artefacts (0/5)
2 | (/)
|  |  | General Risk |  | Contract for Harmon.ie needs to be signed before go-live. Risk of delays, due to missing contract. |  |  |  |  | Medium |  | Actively track vendor |  |  |  |  | 2021-10-01
On track
Actions required
|  | Management attention required | General Risk |  | Not enough resources for operations |  |  |  |  | High |  | Recruting ongoing in different regions |  |  |  |  | 2021-10-15
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M293
M293 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Automated Toxic Tracking for Client-based Assets |  |  | Streamline Compliance |  |  |  |  | Benjamin Warnholz |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 360k€ |  | Spent (as per 03.09.2021) |  |  |  | 34k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 300k€ |  | Budget (labor) |  |  |  | 34k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 60k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 25%
75%
15%
1 | Toxicity baseline dashboard(s)1 integrating additional client data sources in SNOW |  |  | 25% |  | € 180k | Data sources and Tasks identified. High Level Design of target solution is finalized and in alignment. | [6 empty] | Workshops with involved technical teams are partially done and performed in order to finalize task and effort. | [7 empty] | 85%
10%
90%
2 | Adoption of SAM Pro software models and SAM Pro lifecycle definitions in alignment with group toxic definitions (and retirement of related custom tables where possible) |  |  | 15% |  | € 40k | SAM Solution is in development | [6 empty] | Implement technical prerequisites to perform normalization. | [7 empty] | 5%
95%
0%
3 | Toxic Asset Management process documentation, incl. the interface to the SAM process regards normalization, software models, lifecycle definitions, etc. |  |  | 10% |  | € 60k | documentation requirements are identified. | [6 empty] | Finalize toxic process and interface definition. | [7 empty] | 100%
4 | User Training Material (e.g., presentation) |  |  | 5% |  | € 20k | Training conecpt is in preperation. | [6 empty] | align on training concept and design modules.
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of Toxic Asset Dashboard including client IT asset data (e.g. AVC, AMC, fat client, smart mobile de-vices) for minimum of 25 OEs (0/25)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M294
M294 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Integrated Information Risk Management early Live​ |  |  | Streamline Compliance |  |  |  |  | Michael Habel |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 650k€ |  | Spent (as per 03.09.2021) |  |  |  | 123k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 650k€ |  | Budget (labor) |  |  |  | 123k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 25%
75%
40%
1 | Harmonized scoping questionnaires integrated with existing CIA assessments |  |  | 25% |  | € 160 k | - Process for a two-staged scoping process designed and aligned - Discussion with AGCS regarding specific evaluation process started - First implications of VAIT amendment on Risk Management analysed | [6 empty] | - Align on two-staged scoping process with Group IS Function and Group CIO - Finalize analysis existing scoping methodologies for ITOM & ISMS and protection requirement anaylsis | [7 empty] | 60%
25%
75%
2 | Additional training material and sessions for IIRM (early live support) |  |  | 40% |  | € 130 k | - All ITOM hands on sessions performed - Building blocks and structure for stakeholder specific trainings defined and aligned | [6 empty] | - Reporting and Dashboards for IIRM Risk management N25 to be aligned - Continuous OE communication and support ongoing | [7 empty] | 20%
80%
10%
3 | Design “internal” CIO and ISO IIRM KPIs |  |  | 25% |  | € 55 k | - CIO and ISO KPIs drafted | [6 empty] | - KPIs to be aligned | [7 empty] | 90%
4 | IT and IS EGRC Control Center and Interface is handed over to AZTech GRC Service |  |  | 20% |  | € 205 k | - Service transitionplan including hand over and shadowing phase created and communicated to EGRC Service - Technical skills for technical Service Ressource defined and communicated | [6 empty] | - Align on scope of the 1st and 2nd level support for the EGRC Team - Find Technical Ressource for hand over at GRC Service
5 | Cloud assessment training and rollout to all 60 OEs |  |  | 10% |  | € 100 k | - the cloud assessment communication concept is drafted - technical Archer implementation finally tested, simplification triggered | [6 empty] | - Align cloud assessment stakeholder concept. - Operationalize the cloud assessment stakeholder concept - Start with cloud assessment trainings / roll out sessions
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | General Risk |  | Artefact 4: Currently the GRC Service team does not have a ressource woith the suitable technical skills for the hand over of teh EGRC interface and cockpit. Hand Over activities on hold and delayed. |  |  |  |  | Medium |  | GRC Service Manager is searching for a suitable ressource. A meeting with Gerhard Schneider and Carsten Scholz is scheduled to align on the issue. |  |  |  |  | asap 20/09
1 | # of reached milestones (0/5)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M295
M295 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Global Security Platform GITSO blueprint |  |  | Streamline Compliance |  |  |  |  | George Dietrichsbruckner |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 300k€ |  | Spent (as per 03.09.2021) |  |  |  | 42k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 298k€ |  | Budget (labor) |  |  |  | 42k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 2k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 11%
89%
13%
1 | Key Performance Indicator for each of the 6 selected Security Services |  |  | 11% |  | €48 k | Security Service KPI vetting process determined and relevant stakeholder contact lists coompiled. | [6 empty] | comparison with ITSOA KPIs to determine adequacy; | [7 empty] | 87%
0%
100%
2 | Service Level Agreement vetting draft for each of the 6 selected Security Services |  |  | 13% |  | € 180 k | comparison ITSOA with MSA (partially done) to determine gaps to be considered in service descriptions; exchange with AZ TEC IT Service Description Repair Team on new service description format and structure (scheduled for 16.September). | [6 empty] | exchange with IT Service Description repair team and determination of synergies and service level gaps for Global Security Services; | [7 empty] | 0%
100%
0%
3 | IS Implementation Guidance for Secure System Configuration Management |  |  |  |  | € 26 k | [15 empty] | 100%
4 | Analysis of AFRIS for control gaps in relations to Gearshift with Focus on SSP-OE relationship |  |  |  |  | € 44 k
5
|  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
KPI |  |  | Artefact Risk |  | infomation/documentation/contracts not readily available; requests lenghty and SMEs/owners on holiday leave. |  |  |  |  | Medium
ID | KPI Description (Actuals/Target)
1 | # of KPI + SLA vetting draft for 6 Security Services (0/12)
2 | (/)
On track
Actions required
Management attention required
* Criticality: |  | High = Major negative impact on artefacts/timline
Create Powerpoint

## M296
M296 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Financial Loss Quantification |  |  | Build Security Organization / Skills |  |  |  |  | Thomas Thuspass |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 400k€ |  | Spent (as per 03.09.2021) |  |  |  | 330k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 400k€ |  | Budget (labor) |  |  |  | 330k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 35%
65%
0%
1 | Evaluation of Financial Quantification of Enterprise Cyber Risk. |  |  | 35% |  | € 350 k | * Modell questionnaires collected from 9/10 OEs. * First test runs of financial quantification model carried out for 6/10 OEs. Test runs for 3 OEs in progress. * Alignment of evaluation criteria for the financial quantification model started. First criterias are already defined. | [6 empty] | * Collection of model questionaires from one remaining OE. * Execution of the test runs of financial quantifaction model for the remaining 4 OEs. * Clarification of last remaining methodological questions with BitSight/Kovrr. * Final definition of evaluation criteria for the financial quantification model. * Evaluation of financial quantification results. | [7 empty] | 100%
0%
100%
2 | Recommendation regarding a group-wide roll-out of the Cyber Risk Quantification approach. |  |  | 0% |  | € 50 k | The start of this measure phase is planned for mid-October. | [6 empty] | Alignment of a recommendation for a group-wide roll-out of the Cyber Risk Quantification approach. | [7 empty] | 0%
100%
0%
3 |  |  |  | 0% | [17 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of OEs evaluated within BitSight financial model (0/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M297
M297 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Measure and Enhance Global Phishing Resilience |  |  | Build Security Organization / Skills |  |  |  |  | Clemens Friedrich |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 995k€ |  | Spent (as per 03.09.2021) |  |  |  | 39k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 720k€ |  | Budget (labor) |  |  |  | 39k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 275k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 25%
75%
20%
1 | Design and Implementation of Cyber Security Awareness OE Dashboards and a normalized metric for security awareness per OE |  |  | 25% |  | € 245 k | ▪Technical integration of reporting data sources to Splunk achieved ▪First MVP for Triage and PhishMe report designed | [6 empty] | ▪Development and integration of normalized KPI for GUA dashboard ▪Customize and enhance MVP for Triage and PhishMe report ▪Integration of benchmarking data | [7 empty] | 80%
25%
75%
2 | Creation of GUA building blocks (e.g., Learning Nuggets) supported by AZ brand storyline and as per IS practice #12 |  |  | 20% |  | € 295 k | ▪Alignment with internal stakeholders (Pilot OEs, GCORE, Group Strategy, Marketing and Distribution) on Global Brand Character concept ▪Finalization of storyline for first learning content ▪Photoshooting conducted for production of visuals for Brand Character (CW36) | [6 empty] | ▪Start of production for first video to introduce Global Brand Character (aimed for CW39/ 40) ▪Drive integration and promotion on internal platforms (Allianz Connect, Information Security Training Hub) | [7 empty] | 15%
85%
0%
3 | Execution of 6 Spear Phishing Campaigns and development of a service concept for enhanced Target Group Phishing as a Service |  |  | 25% |  | € 90 k | ▪First Spear Phishing training conducted in CW36 for Az SE BoM and RACo CEOs ▪First groups of test users for OSINT PoC defined (OSINT = Open Source Intelligence) ▪Pilot OEs in scope: Az Technology, Az France, Az Ireland, Az Germany | [6 empty] | ▪Align with GCOO and GCEO on possible enhancement of target groups and introduction of maturity level ▪Next Spear Phishing training planned for CW 40/ 41 ▪Drive alignment with Works Council on planned OSINT PoC for Germany based entities ▪Start data analysis for generating personalized phishing simulations based on automated OSINT technology | [7 empty] | 100%
4 | Security Services offering enhancement with social media protection solution |  |  | 15% |  | € 90 k | ▪Existing contract extended by 6 months ▪Alignment with internal stakeholders incl. Procurement | [6 empty] | ▪Creation of future pricing model and conditions with Zerofox ▪Preparing OE Roadshows with H4 and Group Communications (GCORE); planned for October
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of learning nuggets and OE dashboards created (0/10)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M298
M298 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Strategic THREAT Intelligence and Resulting risk Identification Program |  |  | Build Security Organization / Skills |  |  |  |  | Thomas Wolf |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 480k€ |  | Spent (as per 03.09.2021) |  |  |  | 101k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 480k€ |  | Budget (labor) |  |  |  | 101k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 2%
98%
10%
1 | Threat Intelligence / cyber risk management strategy |  |  | 2% |  | € 240 k | Hiigh-level Approach aligned | [6 empty] | Alignment with author and ACDC on approach details Stakeholder interviews and alginment Strategy high -> Low level dreation | [7 empty] | 90%
20%
80%
2 | Advanced threats (insider / state-sponsored) strategy |  |  | 10% |  | € 150 k | Approach aligned Document content / structure defined Decepton strategy in clarification / feature expansion | [6 empty] | Stakeholder interviews and alginment Strategy high -> Low level creation Advanced social defense alignment | [7 empty] | 0%
100%
0%
3 | AI model for strategic threat intelligence (PoV) |  |  | 20% |  | € 90 k | Infrastructure alignment done, infrastructure in buildup Data source connection: high-level aligned Test from HY1 evaluated | [6 empty] | Infrastructure completion model integration with data source model improvement | [7 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of reached artefacts (0/3)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M299
M299 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Enforcement of Security Architecture |  |  | Build Security Organization / Skills |  |  |  |  | Jan General |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 430k€ |  | Spent (as per 03.09.2021) |  |  |  | 145k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 430k€ |  | Budget (labor) |  |  |  | 145k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 0%
100%
15%
1 | Gap analysis and enforcement of implementation to secure with API and Container Patterns |  |  | 0% |  | € 135 k | [7 empty] | Determine GAP candidates | [7 empty] | 85%
35%
65%
2 | An architectural view on IS Economics |  |  | 15% |  | € 85 k | Inital workshop on IS Economics methodology performed | [6 empty] | Document and align IS Economics methodology Cluster achitectural controls | [7 empty] | 15%
85%
15%
3 | Event Brokering Security Patterns |  |  | 35% |  | € 90 k | Inital pattern created and workshops to align content prepared | [6 empty] | Workshops to align pattern content | [7 empty] | 85%
4 | Threat modelling deployment and trainings in Allianz Technology |  |  | 15% |  | € 80 k | POC finished | [6 empty] | finish documentation. Determin training content
5 | Moving Enterprise Security Reference Architecture into ADOIT |  |  | 15% |  | € 40 k | Workshop with ADOit perform and approach and technical needs to import Enterprise Security Reference Architecture determined | [6 empty] | Testimport of a limited numbers of controls
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of architectural documents (e.g. pattern / analysis / methodology) published (0/7)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M300
M300 |  | Measure Report - HY2 2021
[11 empty] | Status report is up to date: |  |  |  | Yes |  |  | Help required: |  | No
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Metrics phase @We protect scale up on skills |  |  | Build Security Organization / Skills |  |  |  |  | Samuel Hurst |  |  |  | 01.07.2021 - 31.12.2021 |  |  |  | as per 17.09.2021
[9 empty] | Approved (HY2 2021) |  |  |  | 540k€ |  | Spent (as per 03.09.2021) |  |  |  | 67k€ |  | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 390k€ |  | Budget (labor) |  |  |  | 55k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 150k€ |  | Budget (non-labor) |  |  |  | 12k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done | [6 empty] | 25%
75%
55%
1 | Develop performance metrics to maximize ROI |  |  | 25% |  | 140k€ | All metrics have been agreed with Measure Sponsor. Visualization of metrics proposed, to be aligned in September. | [6 empty] | Monthly reporting of metrics. Final metrics report. | [7 empty] | 45%
25%
75%
2 | Organization and communication of CSAM events |  |  | 55% |  | 110k€ | A panel discussion with P&R, InfoSec, DP and Compliance (tbd) is planned. Also planned is an event with Euler Hermes (one in German to accommodate AZ D, and one in English). | [6 empty] | Comms - updated Group CSAM Connect page and German translation of AZ Tech promotional material. | [7 empty] | 15%
85%
0%
3 | Steering of CoT education initiatives & TrustNet |  |  | 25% |  | 105k€ | Ransomware event organized by the TrustNet community, with speakers from Atos, Critical Impact and BSI. | [6 empty] | Another ransomware event is planned, and also one on mobile security. | [7 empty] | 100%
4 | Mandatory InfoSec eLearning on SuccessFactors |  |  | 15% |  | 20k€ | eLearning modules scoped. HvS have submitted a proposal and quote. HR have been informed about SuccessFactors integration. | [6 empty] | See risk. HvS quote to be reviewed by Measure Sponsor. Once accepted, a PowerPoint will be sent for Anette/Samuel to review and advise of adjustments.
5 | Publication of SPF guideline and quiz |  |  | 0% |  | 15k€ | [7 empty] | See risk. Frank is unlikely to have capacity to achieve KPI but mitigation activities planned.
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | Artefact Risk |  | Publication of SPF guideline and quiz. Frank is at maximum capacity in his Global Mail project (he is taking on both Product Owner and Project Lead responsibilities due to staff shortages). From a business perspective, Global Mail is currently takes strategic priority, however this is delaying progress of the M300 KPI. |  |  |  |  | Medium |  | Frank could seek support from a suitably experienced colleague, with Frank to review. This would help to progress the KPI before the November 2021 deadline. Marina would be ideally placed to cover, however she returns from leave in January 2022. |  |  |  |  | 2021-09-08
1 | # of high qualitative metrics for ROI (0/5)
2 | (/)
|  |  | Artefact Risk |  | Mandatory InfoSec eLearning on SuccessFactors. Anette may not find capacity to lead on the eLearning due to other project commitments. |  |  |  |  | Low |  | Samuel has been supporting Anette with the eLearning and has capacity to cover. |  |  |  |  | 2021-09-08
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint