## Plan view
IT Security Investment Initiative
Progress KPI plan view
Focus Area | # | Measure | Progress KPIs | Baseline 01.01.2021 | Actuals 19.03.21 | Target 30.06.2021 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021
| KPI(1) | M252 | # of entities with secure passwords | 0 | 4 | 6 | 2 | 3 | 4 | 6
| KPI (2) | M253 | # different control access points managed | 0 | 3 | 6 | 1 | 2 | 3 | 6
2. Increase detection | KPI (8) | M259 | # of Cloud log sources onboarded to ACDC | 0 | 6 | 6 | 0 | 2 | 4 | 6
| KPI (9) | M260 | # of integrations or automations | 0 | 10 | 16 | 5 | 8 | 10 | 16
| KPI (16) | M268 | # of design and effectiveness milestones for the described artefacts | 0 | 4 | 7 | 2 | 3 | 6 | 7
| KPI (20) | M264 | # of devices updated | 0 | 5000 | 20000 | 2500 | 5000 | 10000 | 20000
- confidential -
Export KPIs

## M252
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M252 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # of entities with secure passwords
|  | 6 | 2 | 2 | 2 | 1 | 1 | 0 | 2 | 3 | 4 | 6
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 6 | 2 | 2 | 2 | 1 | 1 | 0 | 2 | 3 | 4 | 6

## M253
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M253 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # different control access points managed
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 6
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 6

## M259
| Focus Area | Increase Detection | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M259 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # of Cloud log sources onboarded to ACDC
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 6
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 6

## M260
| Focus Area | Increase Detection | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M260 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # of integrations or automations
|  | 16 | 6 | 5 | 4 | 1 | 1 | 0 | 5 | 8 | 10 | 16
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 16 | 6 | 5 | 4 | 1 | 1 | 0 | 5 | 8 | 10 | 16

## M268
| Focus Area | Streamline compliance | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M268 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # of design and effectiveness milestones for the described artefacts
|  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 6 | 7
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 6 | 7 | - KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021

## M264
[7 empty] | Focus Area | Build Security org/skills | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative | [7 empty] | M264 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 | [7 empty] | # of devices updated
[8 empty] | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 40 | 50
Board Members | H Ressort | ITC Mapping |  | Group Iso Function | OEs ID | CIM ID | OE | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
Bäte | H1 CEO | 1 | Allianz SE, Allianz Europe | Shared Services | 1 | AZSE | Allianz SE | [7 empty] | 0
|  | 2 | TBD | Asset & Overseas | 2 | AU | Allianz Australia P&C | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Thallinger | H3 Investments Management | 2 | Allianz Investment | Shared Services | 3 | ADEUS | ADEUS Aktienregister-Service-GmbH | [7 empty] | 0
|  |  |  | Europe 3 | 4 | AGL | Allianz Global Life | [7 empty] | 0
|  |  |  | Shared Services | 5 | AIM | Allianz Investment Management (AIM) | [7 empty] | 0
|  |  |  | Shared Services | 6 | ARE | Allianz Real Estate (ARE) | [7 empty] | 0
|  |  |  | TBD | 7 | AUL | Allianz Australia Life | [7 empty] | 0
|  |  |  | Shared Services | 8 | IDS | Investment Data Services (IDS) | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Mascher | H4 Operations | 3 | Allianz Technology | AZ Technology | 9 | AMOS | Allianz Technology | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Balbinot | H5 Insurance Western & Southern Europe, AZAP | 4 | AZAP | AZAP | 10 | CNPC | Allianz China - P&C | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 11 | CNH | Allianz China - Holding | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 12 | ID | Allianz Indonesia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 13 | LAPC | Allianz Laos | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 14 | MY | Allianz Malaysia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 15 | PH | Allianz Philippine - L&H | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 16 | LK | Allianz Sri Lanka | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 17 | AS | Allianz Singapore | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 18 | TWL | Allianz Taiwan - Life | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 19 | TH | Allianz Thailand | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 20 | FIN | FinOS - Holding | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H2 Finance, Controlling, Risk | 5 | Allianz Benelux | Europe 2 | 21 | BLX | Allianz Benelux | [7 empty] | 0
| H2 Finance, Controlling, Risk | 6 | Allianz France | Europe 2 | 22 | FR | Allianz France | [7 empty] | 0
| H2 Finance, Controlling, Risk | 7 | Allianz Greece | Europe 3 | 23 | GR | Allianz Greece | [7 empty] | 0
| H2 Finance, Controlling, Risk | 8 | Allianz Italy | Europe 3 | 24 | IT | Allianz Italy | [7 empty] | 0
| H2 Finance, Controlling, Risk | 9 | Allianz Turkey | Europe 3 | 25 | TR | Allianz Turkey | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Theis | H7 Insurance German Speaking Countries & CEE | 10 | Allianz Germany | Europe 1 | 26 | AZD | Allianz Germany | [7 empty] | 0
| H2 Finance, Controlling, Risk | 11 | CEE | CEE | 27 | AT | Allianz Austria (Elementar) | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 28 | BG | Allianz Bulgaria | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 29 | CZ | Allianz Czechia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 30 | HU | Allianz Hungary | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 31 | HR | Allianz Croatia (Zagreb) | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 32 | PL | Allianz Poland | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 33 | RO | Allianz Romania (Tiriac) | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 34 | RU | Allianz Russia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 35 | SK | Allianz Slovakia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 36 | UKR | Allianz Ukraine | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H2 Finance, Controlling, Risk | 12 | Allianz Suisse | Europe 1 | 37 | CH | Allianz Switzerland | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Hunt | H8 Asset Management, USA Life Insurance | 13 | Allianz Asset Management Holding (AAM) | Asset & Overseas | 38 | AAM | Allianz Asset Management Holding (AAM) | [7 empty] | 0
| H2 Finance, Controlling, Risk | 15 | Allianz Global Investors (AGI) | Asset & Overseas | 39 | AGI | Allianz Global Investors (AGI) | [7 empty] | 0
| H2 Finance, Controlling, Risk | 16 | Pacific Invest.Manag. Comp.(PIMCO) | Asset & Overseas | 40 | PIMCO | Pacific Investement Management Company (PIMCO) | [7 empty] | 0
| H2 Finance, Controlling, Risk | 17 | Allianz Life | Asset & Overseas | 41 | USL | Allianz Life US | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Peiris | H9 Global Lines & Anglo Markets, MENA, Africa | 18 | Allianz Africa | AZ Africa | 42 | AFR | Allianz Africa | [7 empty] | 0
|  |  |  | AZ Africa | 43 | MA | Allianz Morocco | [7 empty] | 0
[5 empty] | ∑ | ∑ | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 19 | MENA | MENA | 44 | EGLH | Allianz Egypt L&H | [7 empty] | 0
|  |  |  | MENA | 45 | EGPC | Allianz Egypt P&C | [7 empty] | 0
|  |  |  | MENA | 46 | LB | Allianz Lebanon | [7 empty] | 0
|  |  |  | MENA | 47 | SA | Allianz Saudi Arabia | [7 empty] | 0
[5 empty] | ∑ | ∑ | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 20 | Allianz Global Corporate & Specialty (AGCS) | Europe 1 | 48 | AGCS | Allianz Global Corporate & Specialty (AGCS) | [7 empty] | 0
|  | 21 | Reinsurance | Europe 1 | 49 | AZRE | Allianz Reinsurance | [7 empty] | 0
|  | 23 | Allianz Ireland | Europe 3 | 50 | IE | Allianz Ireland | [7 empty] | 0
|  | 24 | Allianz UK | Europe 3 | 51 | UK | Allianz UK | [7 empty] | 0
|  | 25 | Euler Hermes Group | Europe 2 | 52 | EH | Euler Hermes | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
de la Sota | H10 Business Transformation | 26 | Allianz Ibero & Latin America | IbertoLatAm | 53 | AR | Allianz Argentina | [7 empty] | 0
|  |  |  | IbertoLatAm | 54 | BR | Allianz Brazil | [7 empty] | 0
|  |  |  | IbertoLatAm | 55 | CO | Allianz Colombia | [7 empty] | 0
|  |  |  | IbertoLatAm | 56 | MX | Allianz Mexico | [7 empty] | 0
|  |  |  | IbertoLatAm | 57 | PT | Allianz Portugal | [7 empty] | 0
|  |  |  | IbertoLatAm | 58 | ES | Allianz Spain (Seguros) | [7 empty] | 0
[5 empty] | ∑ | ∑ | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 27 | Allianz Partners | Europe 2 | 59 | AWP | Allianz Partners | [7 empty] | 0
|  | 28 | TBD | Shared Services | 60 | AZX | AllianzX | [7 empty] | 0
[5 empty] | ∑ | ∑ | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0