## Status Overview
ç | IT Security Investment Initiative
| Status overview |  | HY1 2021
# | Focus Area | # | MID | Global Security Initiative Measure | Progress KPIs | (Baseline/Target) | Measure Lead | Approved Budget | Labor | Non-Labor | Risk | Budget | Artefacts | Risk | Budget | Artefacts
1 | Slow down hackers | KPI (2) | M252 | Use strong passwords automated check over all entities | # of entities with secure passwords | (0/6) | Max Müller | 2,500k€ | 2,500k€ | 0k€ |  |  |  | 0 | 0 | 0
2 | Slow down hackers | KPI (3) | M253 | Control access to Allianz infrastructure | # different control access points managed | (0/6) | Alexander Huber | 500k€ | 365k€ | 135k€ |  |  |  | 0 | 1 | 0
8 | Increase detection | KPI (9) | M259 | Put up a firewall | # of Cloud log sources onboarded to ACDC | (0/6) | Lucas Muster | 720k€ | 640k€ | 80k€ |  |  |  | 0 | 0 | 0
9 | Increase detection | KPI (10a) | M260 | Use security software | # of integrations or automations | (0/16) | Lucas Muster | 835k€ | 765k€ | 70k€ |  |  |  | 2 | 0 | 0
16 | Streamline compliance | KPI (17) | M268 | Use strong passwords automated check over all entities | # of design and effectiveness milestones for the described artefacts | (0/7) | Julian | 965k€ | 965k€ | 0k€ |  |  |  | 0 | 0 | 0
20 | Build Security org/skills |  | M264 | Update programs and systems regularly | # of devices updated | (0/50) | Frank | 125k€ | 125k€ | 0k€ |  |  |  | 0 | 0 | 0
- confidential -

## M252
M252 |  | Measure Report - HY1 2021
[11 empty] | Status report is up to date: |  |  |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Use strong passwords automated check over all entities |  |  | Slow down hackers |  |  |  |  | Max Müller |  |  |  | 01.01.2021 - 30.06.2021 |  |  |  | as per 25.06.2021
[9 empty] | Approved (HY1 2021) |  |  |  | 2,500k€ |  | Spent (as per 15.06.2021) |  |  | 923k€ | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 2,500k€ |  | Budget (labor) |  |  | 923k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done |  |  |  |  | 85%
15%
65%
1 | using a combination of capital and lower-case letters, numbers and symbols |  |  | 85% |  | 500k€ | Pre-Test 1 -4 completed Pre-Test 5 in progress | [6 empty] | Complete last pre-test Artefact to be completed in Measure continuation (M274) | [5 empty] | 35%
50%
50%
2 | making it between eight and 12 characters long |  |  | 65% |  | 200k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | Completemitigation steps for 3rd & 4th pre-test Start pre-test 5 mitigations after test completion Artefact to be completed in Measure continuation (M274) | [5 empty] | 0%
100%
0%
3 | avoiding the use of personal data |  |  | 50% |  | 1,500k€ | Vendor contract negotiations running Scoping review by regulators included | [6 empty] | Complete vendor contracting by end of June Have scoping agreed by Group COO Artefact to be completed in Measure continuation (M274) | [5 empty] | 100%
4 | changing it regularly |  |  | 0% |  | 300k€ | [7 empty] | To be done in measure contioinuation (M274)
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of entities with secure passwords (4/6)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M253
M253 |  | Measure Report - HY1 2021
[11 empty] | Status report is up to date: |  |  |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Control access to Allianz infrastructure |  |  | Slow down hackers |  |  |  |  | Alexander Huber |  |  |  | 01.01.2021 - 30.06.2021 |  |  |  | as per 25.06.2021
[9 empty] | Approved (HY1 2021) |  |  |  | 500k€ |  | Spent (as per 15.06.2021) |  |  | 466k€ | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 365k€ |  | Budget (labor) |  |  | 334k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 135k€ |  | Budget (non-labor) |  |  | 132k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done |  |  |  |  | 30%
70%
45%
1 | control physical access to premises and computers network |  |  | 30% |  | 120k€ | Pre-Test 1 -4 completed Pre-Test 5 in progress | [6 empty] | Complete last pre-test Artefact to be completed in Measure continuation | [5 empty] | 55%
10%
90%
2 | restrict access to unauthorised users |  |  | 45% |  | 160k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | Completemitigation steps for 3rd & 4th pre-test Start pre-test 5 mitigations after test completion Artefact to be completed in Measure continuation | [5 empty] | 90%
10%
0%
3 | limit access to data or services through application controls |  |  | 10% |  | 20k€ | Vendor contract negotiations running Scoping review by regulators included | [6 empty] | Complete vendor contracting by end of June Have scoping agreed by Group COO Artefact to be completed in Measure continuation | [5 empty] | 100%
4 | restrict what can be copied from the system and saved to storage devices |  |  | 90% |  | 65k€ | [7 empty] | To be done in measure contioinuation
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # different control access points managed (3/6)
2 | (/)
On track
Actions required
Management attention required
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M259
M259 |  | Measure Report - HY1 2021
[11 empty] | Status report is up to date: |  |  |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Put up a firewall |  |  | Increase detection |  |  |  |  | Lucas Muster |  |  |  | 01.01.2021 - 30.06.2021 |  |  |  | as per 25.06.2021
[9 empty] | Approved (HY1 2021) |  |  |  | 720k€ |  | Spent (as per 15.06.2021) |  |  | 488k€ | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 640k€ |  | Budget (labor) |  |  | 488k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 80k€ |  | Budget (non-labor) |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done |  |  |  |  | 99%
1%
100%
1 | Onboarding of Public Cloud Logs and ITMP (3 components) |  |  | 99% |  | 340k€ | Pre-Test 1 -4 completed Pre-Test 5 in progress | [6 empty] | Complete last pre-test Artefact to be completed in Measure continuation | [5 empty] | 0%
100%
0%
2 | Document best practices for ACDC and other teams/departments related to cloud ( e.g. Public Cloud and ITMP) |  |  | 100% |  | 140k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | Completemitigation steps for 3rd & 4th pre-test Start pre-test 5 mitigations after test completion Artefact to be completed in Measure continuation | [5 empty] | 0%
100%
0%
3 | Technical concept for distributed event sources in format and forwarding methods (e.g., Application logs) |  |  | 100% |  | 160k€ | Vendor contract negotiations running Scoping review by regulators included | [6 empty] | Complete vendor contracting by end of June Have scoping agreed by Group COO Artefact to be completed in Measure continuation (M274) | [5 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of Cloud log sources onboarded to ACDC (6/6)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M260
M260 |  | Measure Report - HY1 2021
[11 empty] | Status report is up to date: |  |  |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Use security software |  |  | Increase detection |  |  |  |  | Lucas Muster |  |  |  | 01.01.2021 - 30.06.2021 |  |  |  | as per 25.06.2021
[9 empty] | Approved (HY1 2021) |  |  |  | 835k€ |  | Spent (as per 15.06.2021) |  |  | 584k€ | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 765k€ |  | Budget (labor) |  |  | 584k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 70k€ |  | Budget (non-labor) |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done |  |  |  |  | 50%
50%
40%
1 | Implement anti-spyware |  |  | 50% |  | 270k€ | Pre-Test 1 -4 completed Pre-Test 5 in progress | [6 empty] | Complete last pre-test Artefact to be completed in Measure continuation | [5 empty] | 60%
60%
40%
2 | Implement anti-malware |  |  | 40% |  | 235k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | Completemitigation steps for 3rd & 4th pre-test Start pre-test 5 mitigations after test completion Artefact to be completed in Measure continuation | [5 empty] | 30%
70%
0%
3 | Implement anti-virus programs |  |  | 60% |  | 40k€ | Vendor contract negotiations running Scoping review by regulators included | [6 empty] | Complete vendor contracting by end of June Have scoping agreed by Group COO Artefact to be completed in Measure continuation (M274) | [5 empty] | 100%
4 | Develop a technical concept and conduct PoC for an Information Security Dashboard and Reporting Service to remove malicious code |  |  | 30% |  | 220k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | To be done in measure contioinuation
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of integrations or automations (10/16)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M268
M268 |  | Measure Report - HY1 2021
[11 empty] | Status report is up to date: |  |  |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Use strong passwords automated check over all entities |  |  | Streamline compliance |  |  |  |  | Julian |  |  |  | 01.01.2021 - 30.06.2021 |  |  |  | as per 25.06.2021
[9 empty] | Approved (HY1 2021) |  |  |  | 965k€ |  | Spent (as per 15.06.2021) |  |  | 694k€ | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 965k€ |  | Budget (labor) |  |  | 694k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done |  |  |  |  | 80%
20%
100%
1 | Using a combination of capital and lower-case letters, numbers and symbols |  |  | 80% |  | 210k€ | Pre-Test 1 -4 completed Pre-Test 5 in progress | [6 empty] | Complete last pre-test Artefact to be completed in Measure continuation | [5 empty] | 0%
40%
60%
2 | Making it between eight and 12 characters long |  |  | 100% |  | 180k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | Completemitigation steps for 3rd & 4th pre-test Start pre-test 5 mitigations after test completion Artefact to be completed in Measure continuation | [5 empty] | 30%
70%
10%
3 | Avoiding the use of personal data |  |  | 40% |  | 280k€ | Vendor contract negotiations running Scoping review by regulators included | [6 empty] | Complete vendor contracting by end of June Have scoping agreed by Group COO Artefact to be completed in Measure continuation (M274) | [5 empty] | 90%
4 | Changing it regularly |  |  | 30% |  | 105k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | To be done in measure contioinuation
5 | Never using it for multiple accounts |  |  | 10% |  | 190k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | To be done in measure contioinuation
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of design and effectiveness milestones for the described artefacts (4/7)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint

## M264
M264 |  | Measure Report - HY1 2021
[11 empty] | Status report is up to date: |  |  |  | Yes
Measure Name: |  |  | Focus Area: |  |  |  |  | Measure Lead: |  |  |  | Measure Duration: |  |  |  | Status:
Update programs and systems regularly |  |  | Build Security org/skills |  |  |  |  | Frank |  |  |  | 01.01.2021 - 30.06.2021 |  |  |  | as per 25.06.2021
[9 empty] | Approved (HY1 2021) |  |  |  | 125k€ |  | Spent (as per 15.06.2021) |  |  | 85k€ | Click this button to create a powerpoint presentation:
Risk
Overall Status |  |  |  | Budget |  |  |  |  | Budget (labor) |  |  |  | 125k€ |  | Budget (labor) |  |  | 85k€
|  |  |  | Artefacts |  |  |  |  | Budget (non-labor) |  |  |  | 0k€ |  | Budget (non-labor) |  |  | 0k€
ARTEFACTS
ID | Artefact Description |  |  | Progress |  | Approved Budget (labor) | Achievements | [7 empty] | Work to be done |  |  |  |  | 25%
75%
55%
1 | Updates contain vital security upgrades that help protect against known bugs and vulnerabilities. |  |  | 25% |  | 50k€ | Pre-Test 1 -4 completed Pre-Test 5 in progress | [6 empty] | Complete last pre-test Artefact to be completed in Measure continuation | [5 empty] | 45%
0%
100%
2 | Implment intrusion detectors to monitor system and unusual network |  |  | 55% |  | 75k€ | Pre-Test 1 + 2 retested Pre-Test 3 -4 mitigation running | [6 empty] | Completemitigation steps for 3rd & 4th pre-test Start pre-test 5 mitigations after test completion Artefact to be completed in Measure continuation | [5 empty] | 0%
100%
0%
3 |  |  |  | 0% | [15 empty] | 100%
4 |  |  |  | 0%
5 |  |  |  | 0%
KPI |  |  | RISK |  | DESCRIPTION |  |  |  |  | CRITICALITY* |  | MITIGATION ACTIVITIES |  |  |  |  | RESOLUTION DATE
ID | KPI Description (Actuals/Target) |  | - | [6 empty] | -
1 | # of devices updated (5000/20000)
2 | (/)
|  |  | - | [6 empty] | -
On track
Actions required
|  | Management attention required | - | [6 empty] | -
* Criticality: |  | High = Major negative impact on artefacts/timline |  |  | Medium = Considerable impact on artefacts/timeline |  |  |  |  | Low = Minor negative impact on artefacts/timeline
Create Powerpoint